## Summary
Project Summary
Project Name | Cassidy Base Schedule
Client | Cassidy & Associates
Location | Washington, DC
Health | red
Baseline Move-In | 2026-09-23
Forecast Move-In | 2026-05-21
Move-In Variance (Days) | -125
Execution Delay (Days) | 0
Blackout Impact (Days) | 3
Order Release Date | 2025-12-12
Next Milestone

## Milestones
Name | Baseline | Forecast | Actual | Variance | Status | Reason | Recommended Action
Award Date |  | 2026-04-08 | 2026-04-08 |  | done | Milestone is completed. | Monitor.
Kickoff Start |  | 2025-11-25 |  |  | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Programming Complete |  | 2025-12-02 |  |  | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Design Start |  | 2025-12-02 |  |  | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Design Complete |  | 2025-12-03 |  |  | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Order Release |  | 2025-12-12 |  |  | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Install Start |  | 2026-03-23 |  |  | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Punch Complete |  | 2026-05-21 |  |  | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Move-In |  | 2026-05-21 |  |  | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.

## Blackout Impact
Milestone | Baseline | Forecast | Blackout Days | Reason

## Execution Drivers
Milestone | Total Variance | Blackout Days | Execution Delay | Reason | Recommended Action

## Warnings
Type | Field | Message | Reason
critical | design_days | design_days is below minimum (1 < 3) | Schedule assumption violates a configured guardrail.
critical | delivery_buffer_days | delivery_buffer_days is below minimum (2 < 14) | Schedule assumption violates a configured guardrail.