## Summary
Project Summary
Project Name | Test Project 001
Client | Test Client
Location
Health | red
Baseline Move-In
Forecast Move-In
Move-In Variance (Days)
Execution Delay (Days)
Blackout Impact (Days)
Order Release Date
Next Milestone

## Milestones
Name | Baseline | Forecast | Actual | Variance | Status | Reason | Recommended Action
Project Awarded | 2026-04-13 | 2026-04-13 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Planning Complete | 2026-04-20 | 2026-04-20 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Procurement Complete | 2026-05-04 | 2026-05-04 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Installation Start | 2026-05-18 | 2026-05-18 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Installation Complete | 2026-05-25 | 2026-05-25 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Punchlist Complete | 2026-06-01 | 2026-06-01 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Final Invoice | 2026-06-08 | 2026-06-08 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.

## Blackout Impact
Milestone | Baseline | Forecast | Blackout Days | Reason
Installation Complete | 2026-05-25 | 2026-05-25 | 1 | Schedule window crosses blackout/non-working dates.

## Execution Drivers
Milestone | Total Variance | Blackout Days | Execution Delay | Reason | Recommended Action

## Warnings
Type | Field | Message | Reason
critical | delivery_buffer_days | delivery_buffer_days is below minimum (2 < 14) | Schedule assumption violates a configured guardrail.