## Summary
Project Summary
Project Name | Dr office
Client | Taylors
Location
Health | red
Baseline Move-In | 2026-12-14
Forecast Move-In | 2026-07-21
Move-In Variance (Days) | -146
Execution Delay (Days) | 0
Blackout Impact (Days) | 5
Order Release Date
Next Milestone

## Milestones
Name | Baseline | Forecast | Actual | Variance | Status | Reason | Recommended Action
Project Awarded | 2026-04-10 | 2026-04-10 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Planning Complete | 2026-04-17 | 2026-04-17 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Procurement Complete | 2026-05-01 | 2026-05-01 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Installation Start | 2026-05-15 | 2026-05-15 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Installation Complete | 2026-05-22 | 2026-05-22 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Punchlist Complete | 2026-05-29 | 2026-05-29 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.
Final Invoice | 2026-06-05 | 2026-06-05 |  | 0 | overdue | Milestone forecast date is before today and the milestone is not complete. | Escalate owner, confirm blocker, and update recovery plan.

## Blackout Impact
Milestone | Baseline | Forecast | Blackout Days | Reason

## Execution Drivers
Milestone | Total Variance | Blackout Days | Execution Delay | Reason | Recommended Action

## Warnings
Type | Field | Message | Reason
critical | delivery_buffer_days | delivery_buffer_days is below minimum (2 < 14) | Schedule assumption violates a configured guardrail.